[image: ]	626 State St., Rm 107
	Erie, PA 16501
	(814) 870-1540



REQUEST FOR QUOTE
Demolition & Site Restoration – 454 E 10th St, Erie, PA
October 28, 2026
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The Redevelopment Authority of the City of Erie (RACE) is accepting proposals from qualified firms to provide structure demolition, site clearance, and site restoration at 454 E 10th St in the City of Erie.

Proposals should be prepared using the form provided and submitted to the RACE offices (Redevelopment Authority of the City of Erie 626 State St., Room 107, Erie, PA  16501 or fax to 814.870.1331) by 12:00 pm on Friday, November 6, 2026.


SCOPE OF WORK

Work to be conducted includes the complete demolition of all existing structure(s), removal and disposal of all debris from the site, backfill, grading, and site restoration.  Work shall be performed in accordance with the General Requirements and Technical Specifications outlined below, and all applicable laws.  

Each project requires the complete demolition of the primary structure, including the removal of any rear sheds, garages, accessory structures, brush overgrowth, dumped materials, and all other debris, with all materials transported and disposed of at licensed disposal facilities. Partial demolition or selective removal will not be accepted.

Work includes the full removal of all above- and below-grade improvements, including foundations, slabs, footings, and basement structures, followed by proper utility abandonment, backfilling, grading, topsoil placement, and seeding to restore each parcel to a safe, stable, and mowable condition.

To wit:

1. Two (2) House structures
2. Front porches
3. Concrete walkway on west side

AWARD OF CONTRACT

RACE intends to award a single contract to the lowest responsible bidder who demonstrates the experience, skill and competence required to perform the required services in the most efficient, cost-effective, and professional manner.  

The agreement between RACE and the successful bidder will incorporate all of the General Requirements and Technical Specifications outlined in this Request for Proposals.

GENERAL REQUIREMENTS

Proposal Form – All bids must be made on the form provided with this Request.  No bid will be considered responsible unless the proper form is completed and properly signed.

Inclusive of All Costs – Bids shall be inclusive of all costs including permits, site work, disposal, equipment, and materials necessary for contractor to provide a complete project. The contractor shall be responsible for applying for and securing all permits and providing copies of those permits to the Erie Land Bank for confirmation of same.

Time for Completion – The contractor will have forty-five (45) days from the date a contract is executed to complete all work required hereunder. Time is of the essence. Contractor shall complete all work within forty-five (45) calendar days of contract execution. Failure to complete the work within the required period shall result in liquidated damages of $100 per calendar day, which the parties agree represents a reasonable estimate of damages and is not a penalty.

In the event that seasonal weather conditions prevent all site restoration work to be completed, contractor may be granted a seasonal extension to complete site restoration only until Spring 2027 when conditions may again allow for new grass seed to sprout. In the event of such an extension, RACE will withhold 10% of the contracted amount pending completion and approval of final site restoration work.


Insurance – The selected contractor shall provide Certificates of Insurance evidencing coverages not less than specified below and specifically naming the Erie Land Bank as an additional insured.

· Workmen’s Compensation Insurance coverage in compliance with the statutory requirements of the Commonwealth of Pennsylvania.


· General Liability insurance with limits no less than – 

· Personal Injury, including Death - $1,000,000 per occurrence
· Property Damage - $1,000,000 per occurrence

General Liability coverage shall also include an endorsement covering all equipment to be used in the performance of the work.

Indemnification – The selected contractor shall be solely responsible for any loss of life, personal injury, or property damage of any kind resulting from contractor’s performance, including, but not limited to, all liability claims in addition to any and all environmental claims arising from the actions and conduct of the selected contractor.

The contractor shall hold harmless, indemnify, and defend the Erie Land Bank and its directors, officers, employees, agents, and successors against any and all claims, suits, losses, and costs of liability on account of injury or death to persons or damage to property caused in connection with contractor’s performance.

Contractor Eligibility - The selected contractor shall be in good standing with the City of Erie and Commonwealth of Pennsylvania; this includes being current for all City of Erie taxes, fines, and assessments, and not being debarred from entering into contracts with agencies of the Commonwealth of Pennsylvania.  

DEMOLITION & SITE RESTORATION TECHNICAL SPECIFICATIONS
Applicable to All Residential Demolitions Conducted for the Redevelopment Authority of the City of Erie and the Erie Land Bank
1. GENERAL REQUIREMENTS: Demolition and Site restoration work shall be performed in full compliance with:
· These Technical Specifications
· City of Erie Demolition Ordinance 41-2020, City Code Chapter 310, and all demolition-related regulations issued by the Department of Code Enforcement
· The City of Erie Property Maintenance Code
· Pennsylvania Uniform Construction Code (UCC)
· PA One-Call Law
· All applicable federal, state, and local laws and regulations
· Occupational Safety and Health Administration (OSHA) regulations and standards
The Contractor is solely responsible for understanding and complying with all City of Erie demolition requirements, including necessary permits, inspections, utility terminations, safety regulations, and final approval procedures.
Failure to comply may result in stop-work orders, rejection of work, back-charges, or disqualification from future bidding.
Contractor shall have sole responsibility for construction means, methods, techniques, sequences, procedures, and site safety.
No work may begin until the Contractor has received Notice to Proceed and submitted all required pre-demolition documentation.
Contractor is responsible for protection of adjacent structures, sidewalks, utilities, and all public infrastructure.
1.1 INSURANCE & RISK ALLOCATION
Prior to issuance of a Notice to Proceed and for the duration of the work, the Contractor shall maintain all insurance required under the Contract Documents.
At a minimum, Contractor shall carry:
· Commercial General Liability Insurance with limits of not less than $1,000,000 per occurrence
· Workers’ Compensation Insurance in accordance with Pennsylvania law
The Redevelopment Authority of the City of Erie and Erie Land Bank shall be named as an Additional Insured on the Contractor’s Commercial General Liability policy for ongoing and completed operations, with coverage that is primary and non-contributory.
Proof of insurance must be submitted and approved before mobilization. Failure to maintain required insurance shall result in suspension of work.
Contractor shall indemnify, defend, and hold harmless the Redevelopment Authority of the City of Erie and Erie Land Bank, and their officers, employees, and agents from and against any claims, damages, losses, liabilities, fines, penalties, and expenses arising out of or resulting from the work, except to the extent caused solely by the negligence of the indemnified parties.
2. PRE-DEMOLITION REQUIREMENTS
2.1 UTILITY TERMINATION & VERIFICATION
Contractor must submit written documentation prior to mobilization and before any demolition activity begins:
1. Water Service Termination – Erie Water Works written confirmation.
2. Gas Service Retirement – Utility provider written verification.
3. Electric Service Retirement – Written de-energization confirmation.
4. Telecom/Communications Retirement – Written provider confirmation.
5. Private Utilities – Contractor must identify and properly abandon any private service lines discovered (fuel lines, abandoned conduits, private gas lines, etc.).
No verbal confirmations or contractor assertions will be accepted.
If any utilities need to be terminated, the Redevelopment Authority of the City of Erie or the Erie Land Bank will pay any costs associated with said termination.
2.2 PA ONE-CALL (811) COMPLIANCE
· Contractor must obtain a valid 811 ticket covering demolition and excavation.
· Ticket must be present on-site and produced upon request.
· Work outside the ticket validity period or scope is prohibited.
· Contractor must honor all utility markings and clearances.
2.3 SEWER CAP REQUIREMENT
· Contractor must install a City-approved watertight plug on the sanitary sewer lateral.
· Contractor must schedule and receive written approval from the City’s Demolition Coordinator before backfill is permitted.
2.4 REQUIRED PRE-DEMOLITION CHECKLIST
Contractor must submit the following for approval prior to scheduling demolition:
· Utility termination verifications (water, gas, electric, telecom)
· PA One-Call ticket
· Sewer cap inspection scheduling
· Adjacent property protection plan
· Dust suppression plan
· Traffic or sidewalk closure requests (if applicable)
· Hazardous material identification report (if present or suspected). Contractor is not responsible for environmental testing unless specifically included in the Contract Documents. Contractor shall report visibly suspect hazardous materials encountered during site inspection or demolition activities.
Demolition may not proceed until all items are approved.
3. DEMOLITION REQUIREMENTS
All demolition operations shall be conducted in accordance with City of Erie Demolition Ordinance 41-2020, including required inspections, safety procedures, dust suppression, and material handling.
3.1 STRUCTURES TO BE REMOVED
Contractor shall demolish and remove ALL structures located on the parcel, including:
Principal Structure
· Entire building
· All additions, porches, decks, enclosed areas, steps, overhangs
· Foundation walls, slabs, and basement structures
Accessory Structures
· Detached or attached garages
· Sheds, storage buildings, workshops
· Carports, lean-tos
· Retaining walls, freestanding walls
· Exterior slabs, patios, pavers, pads
No structure may be left standing or partially removed unless authorized in writing.
3.2 BELOW-GRADE STRUCTURAL REMOVAL
Contractor must remove:
· All footings
· All foundation walls, unless needed for stabilization of neighboring house. Such determination must be made in consultation with the Redevelopment Authority of the City of Erie.
· Slab edges and basement floors
· Piers, posts, columns, masonry fragments
· Any concrete or structural materials extending below grade
Minimum removal depth: 24 inches below finished grade, unless otherwise approved in writing by RACE/ELB.
3.3 SIDEWALKS, WALKWAYS & DRIVEWAYS
Private Areas (must be removed)
· Private sidewalks
· Walkways and paths
· Asphalt or concrete driveways
· Pavers, pads, patios, stoops, steps
· Private slabs of any kind
Remove sub-base materials and restore area with compacted clean fill.
Public Infrastructure
· Public sidewalks and driveway aprons remain, unless written authorization is provided by RACE/ELB or the City.
· If damaged by demolition activities, the Contractor must restore at no cost. NOTE: Contractor shall document existing conditions of adjacent sidewalks, curbs, and public infrastructure prior to mobilization. Failure to provide pre-demolition documentation shall create a rebuttable presumption that damage identified after demolition was caused by Contractor operations.
4. SITE PROTECTION & ENVIRONMENTAL REQUIREMENTS
4.1 DUST, DEBRIS & TRACK-OUT CONTROL
Contractor must maintain:
· Continuous dust suppression (water misting required)
· Debris containment to prevent migration to adjacent parcels
· Prevention and removal of track-out into public streets. Track-out onto public streets shall be removed by the end of each workday or immediately if creating a hazardous condition.
· Barricades or fencing around open excavations
· Contractor shall implement temporary erosion and sediment control measures sufficient to prevent sediment migration onto adjacent properties, sidewalks, streets, or storm sewer systems.
4.2 HAZARDOUS MATERIAL DISCOVERY PROTOCOL
If any of the following materials are encountered:
· Underground or above-ground tanks
· Fuel, heating oil, or propane tanks
· Drums, barrels, or chemical containers
· Suspect asbestos material
· Contaminated soil
· Buried debris or waste
Contractor must:
1. Immediately stop work in affected area
2. Secure the site and protect workers and public
3. Notify RACE/ELB immediately
4. Await further directive
Contractor may not disturb regulated materials without written authorization.
Discovery of regulated or hazardous materials may constitute a change in scope to be addressed by written directive.
4.3 PROTECTION OF ADJACENT PROPERTIES
Contractor is responsible for preventing:
· Damage to neighboring structures
· Undermining of foundations
· Falling debris outside parcel limits
· Damage to adjoining property landscaping or fencing
Repairs resulting from contractor negligence are at the contractor’s expense.
5. SITE CLEARANCE – EDGE-TO-EDGE REQUIREMENTS
Contractor must perform complete edge-to-edge site clearance, including removal of:
· All demolition debris
· Dumped materials and trash
· Tires, scrap metal, loose materials
· Landscaping blocks and foreign objects
· Overgrown brush, vines, and volunteer trees with a diameter of 2” and smaller.
· Remove abandoned fencing, fence posts, and embedded metal unless specifically directed otherwise.
Tree Requirements
· Remove downed, dead, or City-approved hazardous trees as determined by RACE/ELB or the City Forester
· You are authorized to remove trees that would otherwise impede demolition of the structures or sidewalks, walkways, or driveways.
· You are authorized to remove trees that are significantly compromised during demolition.
6. REMOVAL, TRANSPORT & DISPOSAL
6.1 TRANSPORTATION & DISPOSAL
· All debris must be removed promptly and disposed of at licensed facilities compliant with the Pennsylvania Solid Waste Management Act.
· Contractor must submit disposal receipts and weight tickets.
· Contractor remains responsible for all debris until properly disposed of at an approved facility.
6.2 PROHIBITED ACTIONS
· No on-site burning
· No burial of debris or structures
· No crush-and-cover operations
7. BACKFILLING, GRADING & DRAINAGE
7.1 BACKFILL MATERIALS
Backfill shall consist of clean earthen fill or approved crushed and processed concrete meeting the requirements below:
APPROVED BACKFILL OPTIONS
1. Clean Earthen Fill
· Free of trash, debris, organics, metal, wood, asphalt, or frozen material.
· Suitable for compaction and grading purposes.
2. Crushed Concrete Aggregate
· Concrete must be uniformly processed and crushed to a maximum size of 4 inches.
· Recycled concrete shall be free of deleterious materials.
· Material must be free of rebar, wire mesh, asphalt, brick, block, or mixed demolition debris.
· Material must be clean and suitable for controlled fill placement.
· Concrete aggregate may only be used below topsoil and shall not be placed within the upper 12 inches of finished grade.
7.2 BACKFILL PLACEMENT
· Backfill material shall be placed in controlled lifts and compacted uniformly.
· Backfilling shall not begin until the sewer cap has been inspected and approved.
· Crushed concrete may be used to fill former basements, crawl spaces, voids, or excavations where structural bearing is not required.
7.3 FINAL GRADING & SETTLEMENT
· Final grading must provide positive drainage away from neighboring parcels.
· Contractor may raise final grade up to 4 inches above surrounding areas to accommodate settlement. Contractor remains responsible for correcting settlement occurring during the warranty period.
· The upper 12 inches of final grade must be clean earthen fill, topsoil, and restoration materials — no crushed concrete may be exposed at final grade.
8. SITE RESTORATION
· ***Note that during those months of the year when grass will not grow (generally, November-March), contractor may be granted an extension to complete final site restoration work until such time as growing conditions permit. In the event of such an extension, RACE will withhold 10% of the contracted price until such time as the site restoration work is complete and approved.
8.1 TOPSOIL
· Place a minimum of 3 inches of screened topsoil across all disturbed areas
· Topsoil must be free of debris, roots, and stones
8.2 FINAL GRADING
· Parcel shall be fine-graded to a smooth, mowable condition
8.3 SEEDING
· Seed entire site with annual ryegrass
· Apply straw mulch or approved equivalent
· Contractor is responsible for seed establishment and correcting bare areas
9. FINAL CLEANING
Contractor must:
· Remove temporary fencing, equipment, and signage
· Clean sidewalks, curbs, and public streets
· Remove track-out and sediment controls after stabilization
10. FINAL INSPECTION & ACCEPTANCE
10.1 SCHEDULING REQUIREMENTS
Contractor must provide:
· Minimum three business days’ notice for final inspection request
· All prerequisites must be completed prior to scheduling
· As requested, contractor shall provide date-stamped pre-demolition and post-demolition photographs documenting site conditions and completed restoration work.
10.2 ACCEPTANCE STANDARDS
To receive approval, the site must be:
· Fully cleared edge-to-edge
· Properly graded and restored
· Free of debris, hazards, and Property Maintenance Code violations
· Properly seeded and mulched
· Compliant with all utility termination requirements
· Accompanied by all required documentation
10.3 REQUIRED CLOSE-OUT SUBMITTALS
· Sewer cap approval
· Utility termination and retirement confirmations
· PA One-Call ticket(s)
· Disposal receipts and weight tickets
· Lien waivers
· One-year warranty acknowledgement
11. WARRANTY REQUIREMENTS
Contractor shall provide a one-year warranty covering:
· Settlement correction
· Regrading
· Topsoil replacement
· Reseeding and stabilization
· Any deficiencies caused by inadequate demolition or restoration
Contractor must correct all deficiencies within 10 business days of notification. If Contractor fails to correct deficiencies within the required timeframe, Owner may perform corrective work and deduct costs from amounts due or pursue recovery from Contractor and/or surety.




BIDDER INFORMATION & PROPOSAL FORM
STRUCTURE DEMOLITION & SITE RESTORATION
454 E 10th St Erie, PA
Sealed Bids Due: November 6, 2026

REQUIRED FOR ALL PERSONS OR ORGANIZATIONS RESPONDING TO A REQUEST FOR PROPOSAL (RFP):

Name of Company:									
Address:										
											
Phone:											
Person Responsible for 
Proposal:										
Title:											
Email address:										
Federal Tax ID (or SS# if 
Individual):										



PRICE QUOTE:										
(Lump sum amount to provide complete demolition, and site restoration services, as detailed in the Request for Proposals.)


											
Authorized Signature
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